## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group S | Completed | 8
Project title | CUT Lost & Found Sytem | In Progress | 1
Stakeholder or organisation | Central University of Technology (CUT) | Not Started | 0
Group mentor | Ms Mbhele | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | August - September 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 95% | Contribution Summary | Count
Main achievement | Finding the stakeholder faster than we thought and actually finishing Phase 1 according to the time frams. The group has developed the initial project concept, scope, requirements, system technologies and project documentation. Understanding the stakeholder's requirements and finalising everything before the given period. | Contribution entries | 6
Main challenge | Confirm stakeholder requirements, and update the project schedule and working against the time. | Verified entries | 6
Next planned activity | Showcasing our project in pictures and diagrams (UML & ERD diagrams) to our lecturers, updating the SRS and the mocrosoft project according to Phase 2 | Unverified entries | 0
|  | Stakeholder engagements | 4

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Katu AJ, NH Khosa, EB Mmakola | 2026-08-19 | 2026-08-20 | Completed | 100 | Initial Meeting notes | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Katu AJ | 2026-08-24 | 2026-08-25 | Completed | 100 | Worked Activity 1.1 Document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | NH Khosa | 2026-08-24 | 2026-08-26 | Completed | 100 | SRS Document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Katu AJ, | 2026-08-20 | 2026-08-21 | Completed | 100 | Interview Questions Document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | NH Khosa | 2026-08-24 | 2026-08-27 | Completed | 100 | SRS Document | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Katu AJ, NH Khosa | 2026-08-28 | 2026-08-30 | Completed | 100 | Initial SRS Document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | SM Zungu, CT Zikalala | 2026-08-28 | 2026-09-04 | Completed | 0 | Microsoft Project | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | NH Khosa | 2026-08-26 | 2026-08-26 | Completed | 100 | Link/SRS Document | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | EB MMAKOLA, BL Makwele |  |  | In Progress | 0 |  | Yes |  | On Track
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Katu AJ, NH Khosa, EB Mmakola, CT Zikalala, SM Zungu, BL Makwele. | 2026-09-02 | 2026-09-03 | Completed | 100 | Progress Tracker | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | NH Khosa | 2026-09-03 | 2026-09-04 | Completed | 100 | Progress Tracker | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))
Progress Flag = IF([Task Description]=O10,"",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Khosa NH | 222002087 | Unit 1 / Phase 1 | 1 & 2 | Finalizing the SRS, work on the Progress report, conducting the feasibility study and risk register, created the Github repository link, updating the final presentation and setting up meetings with the stakeholder | SRS finalized, Github repository created, the progress report is filled in, the final presentation updated and the meetings were successful | 2026-09-02 | 9 | Github linK, SRS, Progress Report | Yes | 2026-09-04 | Everything assigned was completed within the time frames, meetings were successful
AJ Katu | 220044317 | Unit 1 / Phase 1 | 1 & 2 | Initializing the SRS and working through a progress report, conducting the questions for the stakeholder and taking notes in the meetings | Questions that were created are all answered and the SRS file is complete | 2026-09-02 | 6 | SRS, Progress Report | Yes | 2026-09-04 | The questions were answered and had successful SRS completion
EB Mmakola | 224031692 | Unit 1 / Phase 1 | 1 & 2 | Forming a presentation and managed constant communication regarding the short deadlines between our tasks | Presentation was a success and well conducted | 2026-08-30 | 8 | Presentation, SRS | Yes | 2026-09-04 | Communication throughout helped and setting short deadlines
SM Zungu | 224066331 | Unit 1 / Phase 1 | 2 | Creating a Microsoft Project File | Microsoft Project File was complete | 2026-09-04 | 7 | Microsoft Project | Yes | 2026-09-04 | The file was complete and records all our time frames
CT Zikalala | 224047638 | Unit 1 / Phase 1 | 2 | Working together in creating Microsoft Project to keep track of our movements | Microsoft Project File was complete | 2026-09-04 | 7 | Microsoft Project | Yes | 2026-09-04 | The file was complete and records all our time frames
BL Makwele | 219013255 | Unit 1 / Phase 1 | 1 & 2 | Presenting part our project to the stakeholder and creating a formal presentation for both our lecturers and stakeholders | Presentation was a success and well conducted | 2026-08-30 | 8 | Presentation, SRS |  |  | Presentation is complete .

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-24 | Unit 1 / Phase 1 | Meeting | Meeting the stakeholder for the first time and proposing our project to them. | Khosa NH, Katu AJ , B Mmakola | Protection Services officers, Senior Assistant and Director | How broad the Protection Services sector is and knowing the people we will be working with. Getting the requirements of the stakeholder. | confirm stakeholder interview/requirements session and validate assumptions | Stakeholder interview questions/SRS Document
2026-08-26 | Unit 1 / Phase 1 | Meeting | Formal first pitch/meeting of our project and understanding the stakeholder's requirements | Khosa NH, Katu AJ , EB Mmakola, BL Makwele, SM Zungu, CT Zikalala | Directore of Protection Services | Finding how our peoject will come in handy for the Protection Services since they don't have a website or an app for their own sector. | Recording all the requirements that’s the stakeholder puts on the table and working around it. | SRS Document
2026-08-26 | Unit 1 / Phase 1 | Meeting | Getting the real data from the Protection Services offices and real life information/lost items so that we won't work on assumptions | Khosa NH, Katu AJ, EB Mmakola, BL Makwele, SM Zungu, CT Zikalala | Senior Assistant of Protection Services | The real life data and information on lost items and asking the questions, to complete our SRS | Getting all the answers and information we need regarding the Protection Services Current Processes | Presentation
2026-08-27 | Unit 1 / Phase 1 | Meeting | Finalising the requirements with the stakeholder and showing our project schedule that we are working on | Khosa NH, Katu AJ, EB Mmakola, BL Makwele, SM Zungu, CT Zikalala | Director of Protection Services | Verification of the requirements since we had all the data and real information that could work on. | Bringing in all the data that we got from the offices and confirming with the stakeholder of the requirements | Presentation

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-25 | Unit 1 / Phase 1 | Coordinating the group's documentation and project activities | Some activities required review and coordination before completion. | Divide responsibilities clearly, use a shared task list, and review progress regularly | All students | 2026-09-01 | Resolved
2026-08-27 | Unit 1 / Phase 1 | Stakeholder requirements still needed to be confirmed | Some requirements may change after stakeholder feedback. | complete stakeholder engagement and update the SRS based on validated requirements | All students | 2026-09-02 | Resolved
2026-08-29 | Unit 1 / Phase 1 | Technical planning for Flutter, ASP.NET, and Supabase requires alignment | Integration decisions could affect later development | Define component responsibilities and confirm the integration approach before development | EB Mmakola | 2026-09-04 | In Progress
2026-08-26 | Unit 1 / Phase 1 | Identifying the existing manual Process | In order to build the improvement, we needed to understand the foundation | Understanding how thw manual process works in order to build on top of it | All students | 2026-08-30 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | August - September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The group defined the problem, project aim, objectives, and scope, documented the current process, prepared requirements, identified project risks, and developed initial SRS and technology documentation, Github repository, Microfoft Project and the final SRS document. | Stakeholder engagement recorded | Yes
What remains incomplete? | Initial Supabase project | Challenges and actions updated | Yes
Why is it incomplete? | Final coordination of group evidence and documentation | Group reflection completed | Yes
Which contributions were particularly important? | Requirements analysis, project scope definition, SRS development, technology research, and risk identification were particularly important contributions. | Microsoft Project updated | Yes
Were there participation concerns? | No major participation concern has been identified at this stage. Responsibilities have been divided among members, with progress to be reviewed regularly. | GitHub evidence available | Yes
What will the group improve in the next phase? | The group will improve task coordination, maintain clearer evidence for each contribution, confirm requirements earlier, and update the shared schedule more consistently. | Confidential peer check completed | No
Main priority for the next phase | Confirm stakeholders' requirements and complete Phase 1 documentation and evidence.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | CUT Lost & Found System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important learning was that a successful software project requires a clear understanding of the problem before development begins. The group learned that requirements, stakeholder needs, scope, risks, and technical decisions must be documented clearly so that the proposed solution can address the actual problem | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group developed a shared understanding of the Lost and Found problem and produced the initial project scope, requirements, risks, and SRS content. Dividing the documentation and research activities among members helped the group make steady progress while allowing each member to contribute to different aspects of the project. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The main difficulty was coordinating different sections of the project and ensuring that the documentation remained consistent. Stakeholders' requirements also needed to be confirmed, which means that some assumptions may need to be revised before the next phase. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided into project planning, current-process analysis, requirements, risk identification, technical research, and documentation review. Members were expected to provide evidence for their completed work and review the group's overall output.
Did all members contribute fairly? Explain. | At this stage, the group has not identified a major unfair contribution issue. Members have contributed to planning, research, requirements, documentation, and review. The contribution record will continue to be updated so that participation remains transparent.
How did the group handle disagreements or delays? | The group managed delays by communicating about outstanding work, dividing responsibilities, and setting short target dates. Where information was not yet confirmed, the work was recorded as in progress rather than being treated as completed.
What did the group learn from the stakeholder? | The project work highlighted the importance of understanding how lost property is currently reported, recorded, verified, and returned. This will help the group ensure that the proposed system is practical for both students and the protection service.
Improvement action 1 for the next phase | Improve the consistency of task updates and evidence recording after each project activity.
Improvement action 2 for the next phase | Complete stakeholder validation and use the feedback to finalise the requirements and SRS.
Priority for the next phase | The priority for the next phase is to validate the requirements and establish a clear system architecture and design that can guide development.